## Sheet1
Related User Story | Task Description | Initial Estimate | Time Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
view entire inventory | Implement Home UI that will contain a list of all locations and items | 1 | 12 | 8 | 4 | 0
view item location | Implement UI for VIew Item and contains item location | 1
add new item | Implement behavior of Add Item button | 1
create new location | Implement a new location when adding an item and setting location | 1.5
remove item from inventory | Implement removeItem method in Inventory class | 0.5
search for specific item | Implement search field and button UI/behavior | 1
search for specific item | Implement searchItem method in the Inventory class | 0.5
edit item page | Implement Edit Item page UI | 1
edit item button | Implement edit item button behavior and save changes button behavior | 1
edit item details | Implement TextArea for Details when editing an item to add specific notes | 0.5
add/decrease item quantity | Implement item quantity method to increase or decrease item count | 0.5
view items by room | Implement location list with items in each on Main Inventory page | 0.5
mark item as important | Implement CheckBox for items with isSelected method, when editing or adding item | 1
update item location | Implement location dropdown selection for items | 1
share inventory with household | Implement Share Inventory button behavior on Main Inventory page | 1
share inventory with household | Implement behavior to generate and display share link for access | 1
assign container to specific location | Implement Location dropdown on Add Container page | 1
page navigation | Implement Home button and behavior to each page allowing return to Main Inventory page | 1
| Estimate Totals | 16 | 12 | 8 | 4 | 0